## Sheet1
Number | Start | End | Task | Notes
1 | 2022-01-27 | 2022-02-03 | model system dynamics | as per literature and linearized model
2 | 2022-02-04 | 2022-02-11 | parameter estimation
3 | 2022-02-12 | 2022-02-19 | system identification
4 | 2022-02-20 | 2022-02-27 | model-reference adaptive control | integral reinforcement learning
5 | 2022-02-28 | 2022-03-06 | begin project report | establish format, add content from tasks 1 to 4 so we have something and we aren't cramming everything into the report last minute
6 | 2022-03-07 | 2022-04-03 | implement other control structures | overlap is intentional. Additional control structures to be determined as the course progresses, - model free control
7 | 2022-03-20 | 2022-04-10 | control structure comparison | determine which control structures perform best and under which conditions / constraints / requirements
8 | 2022-04-11 | 2022-04-18 | finalize project report | add content from comparison of other control structures
9 | 2022-04-19 | 2022-04-19 | submit project | report + source code